HealixCare HMS

Project Management Plan

| Property | Value |
| --- | --- |
| Version | 1.0 |
| Status | Draft — For Review |
| Date | July 2026 |
| Document Owner | Product Management / PMO |
| Grounded In | 12-document set: Product Vision, Scope & Module Roadmap, Feature Backlog, Role Matrix, Solution / Application / Integration / Security / Deployment / Data Architecture, HMS Technical Documentation, Auth & Security Design |
| Codebase Baseline | hospital-management-system as of 2026-06-24 |
| Companion Artifacts | HealixCare_HMS_Backlog_Workbook.xlsx (live backlog & risk register); Interactive Project Dashboard (HTML) |
| Classification | Confidential |

Table of Contents

# 1. Project Charter

## 1.1 Purpose

This plan defines how the HealixCare HMS product is managed from its current state — a feature-complete modular monolith serving hospitals in both SaaS and on-premise modes — through Phase 2 hardening and the Enterprise roadmap. It converts the documentation set into an actionable management structure: milestones, backlog governance, roles, risk management, and cadence.

## 1.2 Vision (from Product Vision Document)

To give hospitals, clinics, and diagnostic centers of any size a single, secure, unified digital platform connecting every clinical, operational, and financial workflow — from registration to discharge billing — so care teams spend less time on administration and more time on patients.

## 1.3 Current State Summary

- 29 modules inventoried: 22 Complete, 6 Partial (Inventory, HR/Staff, Payroll, Staff Portal, MIS, plus router migration), 1 Stub (Telemedicine).

- Backend: FastAPI modular monolith, 121 PostgreSQL tables, 35 layered module packages plus 30 legacy routers awaiting migration.

- Dual deployment: on-premise (single-tenant, license-enforced) and SaaS (multi-tenant via control plane) from one codebase.

- Security shipped: JWT with server-side revocation, bcrypt cost 12, OTP 2FA, configurable RBAC (role_permissions), facility scoping, PHI field encryption, rate limiting, audit trail.

- Integrations live: Razorpay (webhook-verified), TPA framework, ABHA/ABDM, Claude AI clinical decision support, SMS/WhatsApp notifications.

## 1.4 Success Criteria for This Plan Horizon (6–12 months)

- All 6 Partial modules promoted to Complete.

- Operational readiness closed: automated backups with tested restores, monitoring stack live, SaaS tenant migration process automated.

- Security posture externally validated: PHI encryption coverage documented, third-party penetration test completed.

- High-traffic legacy routers (billing, pharmacy, lab) migrated to modules/; no new code added to routers/.

- Backlog workbook maintained as single source of truth; every shipped item traced back to it.

# 2. Scope Management

## 2.1 In Scope (This Plan Horizon)

Phase 2 hardening (6 module gaps), Phase 2 technical debt (router migration of billing/pharmacy/lab, duplicate-patient detection), operational readiness (backups, monitoring, SaaS migrations), and security/compliance closure (PHI verification, auditor role, secret rotation, pen test). Enterprise items are planned but scheduled after Phase 2 exit criteria are met.

## 2.2 Explicitly Not Planned (Guard Against Scope Creep)

- Native iOS/Android apps — the Mobile API deliberately serves the responsive web frontend.

- Distributed job queue (Celery/Redis) — single-process APScheduler accepted at current scale.

- WebSocket/real-time updates — polling via TanStack Query is the deliberate approach.

- Automated billing rules/bundle pricing engine — bills remain manually itemized.

- Generic cross-hospital health information exchange and direct medical-device integrations (per Vision non-goals).

Any stakeholder request matching this list is rejected by default; overriding requires a documented decision by the Product Owner recorded in the decision log.

# 3. Milestones & Phasing

Dates assume the current team continues at present capacity; adjust at the first monthly review. Each milestone has exit criteria — a milestone is not “done on the date”, it is done when criteria pass.

| Milestone | Window | Contents (Backlog IDs) | Exit Criteria |
| --- | --- | --- | --- |
| M1 — Operational Readiness | Jul–Aug 2026 | P2-09 backups, P2-10 monitoring, P2-11 SaaS migrations, P2-12 PHI verification, P2-13 auditor role | Restore drill passed; dashboards live; tenant migration runbook executed once; PHI coverage doc signed off |
| M2 — Hardening Wave 1 | Sep–Oct 2026 | P2-01 inventory reorder, P2-02 drug expiry job, P2-07 router migration (billing/pharmacy/lab), P2-14 secret rotation | Inventory & Pharmacy modules marked Complete; migrated routers serving production traffic |
| M3 — Hardening Wave 2 | Nov–Dec 2026 | P2-03 attendance, P2-04 payroll calc, P2-05 staff portal, P2-06 MIS dashboards, P2-08 duplicate detection, P2-15 pen test | All Partial modules Complete; pen test report received and remediation items ticketed |
| M4 — Enterprise Wave | H1 2027 | EN-01 telemedicine video, EN-02 remaining migration, EN-06 integration utilities, EN-08 HA, EN-09 frontend splits | Prioritized at M3 review against sales pipeline demand |

# 4. Backlog Governance

- The Backlog Workbook (companion .xlsx) is the single source of truth for classification, priority, and status. The Feature Backlog document is revised from it, not the other way around.

- Each backlog row becomes one ticket in the tracker (GitHub Projects/Jira). Ticket ID = workbook ID (P2-xx / EN-xx).

- Definition of Done per item: code merged to modules/ structure (never routers/), acceptance criteria pass, migration scripts in alembic/, docs updated, deployed to staging, and the workbook row moved to Done.

- New requests enter as candidate rows with Phase = Unclassified; the Product Owner classifies them at the weekly review against the Vision and the Not-Planned list.

- When an item ships, the Feature Backlog document Section 2 (Already Shipped) is updated at the next revision, citing the file path — preserving the codebase-grounded style of the documentation set.

# 5. Roles & RACI

Adapt names to your actual team; roles may be shared by one person in a small team, but each decision needs exactly one Accountable.

| Activity | Product Owner | Tech Lead / Architect | DevOps | Security / Compliance |
| --- | --- | --- | --- | --- |
| Backlog prioritization | A / R | C | C | C |
| Architecture decisions (ADRs) | C | A / R | C | C |
| Router→modules migration | I | A / R | I | I |
| Backups, monitoring, SaaS migrations (M1) | I | C | A / R | C |
| PHI verification, pen test, secret rotation | C | C | C | A / R |
| Release approval | A | R | R | C |
| Risk register upkeep | R | C | C | A |

# 6. Risk Management

The live register (14 risks) is in the Backlog Workbook — Risk Register sheet. The top exposure summary:

| ID | Risk | Severity | Response |
| --- | --- | --- | --- |
| R-01 | No automated backup schedule codified in the repo | Critical | Mitigate first — M1, P2-09; run a restore drill, not just a backup job |
| R-03 | No monitoring stack deployed; metrics exposed but unconsumed | High | Mitigate — M1, P2-10 |
| R-02 | SaaS tenant migration process undocumented | High | Mitigate before tenant growth — M1, P2-11 |
| R-04 | PHI encryption coverage unverified vs. compliance claims | High | Verify & document — M1, P2-12; until then, do not cite coverage to customers |
| R-06 | No third-party pen test on file | High | Commission — M3, P2-15 |
| R-09 | 100K+ line frontend files slow velocity | Medium | Plan splits — M4, EN-09 |

Review the full register monthly; any risk whose likelihood or impact changes gets re-scored and, if needed, a new backlog item.

# 7. Cadence & Reporting

- Weekly (30 min): board review — status changes in the workbook/tracker, blockers, new candidate items classified.

- Monthly (60 min): milestone check against exit criteria, risk register review, dashboard walkthrough, scope-change decisions logged.

- Per release: update Feature Backlog doc Section 2, tag the repo, refresh the Module Inventory maturity column.

- Documentation rule inherited from the doc set: every architecture claim must be grounded in a file path in the codebase. Keep this discipline for all new documents.

# 8. Document Map

Hierarchy per the Product Vision Document, with this plan and its companions added:

| Document | Role in the Hierarchy |
| --- | --- |
| Product Vision Document | Top of hierarchy — every scope decision is tested against it |
| HMS Scope and Module Roadmap | As-built module inventory and phase definitions |
| Feature Backlog with Priority | Narrative backlog; revised from the Backlog Workbook |
| Role Matrix and Permission Catalog | RBAC as implemented; input to security work items |
| Solution / Application / Integration / Security / Deployment / Data Architecture | As-built technical reference; sources of the operational-readiness and debt items |
| Project Management Plan (this document) | Management layer: milestones, governance, RACI, cadence |
| Backlog Workbook (.xlsx) | Live single source of truth for items, module maturity, risks |
| Interactive Project Dashboard (HTML) | At-a-glance status view generated from the same data |

# 9. Document Control

| Field | Value |
| --- | --- |
| Owner | Product Management / PMO |
| Status | Draft v1.0 |
| Review cycle | Monthly, at the milestone review |
| Next revision trigger | M1 exit or any scope-change decision |